## taigaReport_userstories
id | ref | subject | description | sprint_id | sprint | sprint_estimated_start | sprint_estimated_finish | owner | owner_full_name | assigned_to | assigned_to_full_name | assigned_users | assigned_users_full_name | status | is_closed | back-points | design-points | front-points | ux-points | total-points | backlog_order | sprint_order | kanban_order | created_date | modified_date | finish_date | client_requirement | team_requirement | attachments | generated_from_issue | generated_from_task | external_reference | tasks | tags | watchers | voters | due_date | due_date_reason
2974592 | 1 | Cadastro do usuÃ¡rio | Eu como um usuÃ¡rio osso me cadastrar no aplicativo para que tenha acesso Ã s funcionalidades especÃ­ficas para usuÃ¡rio cadastrado. | 242124 | Sprint 1 | 2019-09-16 | 2019-10-07 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 5.0 |  | 5.0 |  | 10.0 | 1568667736006 | 2 | 1568667736003 | 2019-09-16 21:02:16.018886+00:00 | 2019-10-15 13:33:23.809072+00:00 | 2019-10-15 13:26:15.874706+00:00 | False | False | 0 |  |  |  | 2,3,4,5 |  | [] | 0
2974604 | 6 | Pesquisa de Deputados | Sendo um usuÃ¡rio do aplicativo posso pesquisar os deputados | 242124 | Sprint 1 | 2019-09-16 | 2019-10-07 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 20.0 | 5.0 | 13.0 | 2.0 | 40.0 | 1568668080643 | 0 | 1568668080642 | 2019-09-16 21:08:00.670252+00:00 | 2019-10-15 13:31:56.820981+00:00 | 2019-10-15 13:26:45.660156+00:00 | False | False | 0 |  |  |  | 7,8,9,10 |  | [] | 0
2974621 | 12 | Login de usuÃ¡rio | Sendo um usuÃ¡rio do aplicativo posso fazer login com meu usuÃ¡rio e senha para que tenha acesso Ã s funÃ§Ãµes especÃ­ficas de usuÃ¡rio logado. | 242124 | Sprint 1 | 2019-09-16 | 2019-10-07 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 13.0 |  | 2.0 |  | 15.0 | 1568668804459 | 1 | 1568668804458 | 2019-09-16 21:20:04.480467+00:00 | 2019-10-15 13:32:55.709475+00:00 | 2019-10-15 13:27:46.821953+00:00 | False | False | 0 |  |  |  | 13 |  | [] | 0
3011029 | 14 | Envio de notificaÃ§Ãµes | Envia notificaÃ§Ãµes para os usuÃ¡rios | 242125 | Sprint 2 | 2019-10-08 | 2019-10-29 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 40.0 |  |  |  | 40.0 | 1571146634109 | 1 | 1571146634107 | 2019-10-15 13:37:14.129855+00:00 | 2019-10-15 13:37:22.880339+00:00 |  | False | False | 0 | [5 empty] | [] | 0
3011032 | 15 | Modelagem de dados notificaÃ§Ãµes | Modelagem dos dados no banco referente aos itens de notificaÃ§Ãµes, exemplo Eventos e ProposiÃ§Ãµes | 242125 | Sprint 2 | 2019-10-08 | 2019-10-29 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 8.0 |  |  |  | 8.0 | 0 | 2 | 1571146709864 | 2019-10-15 13:38:29.890553+00:00 | 2019-10-15 13:54:02.107111+00:00 |  | False | False | 0 | [5 empty] | [] | 0
3011044 | 16 | Tela lista de deputados | Mostra a lista de deputados e realiza pequisa | 242125 | Sprint 2 | 2019-10-08 | 2019-10-29 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 20.0 |  | 20.0 |  | 40.0 | 1 | 3 | 1571146777061 | 2019-10-15 13:39:37.090685+00:00 | 2019-10-15 13:41:38.682863+00:00 |  | False | False | 0 | [5 empty] | [] | 0
3011049 | 17 | Tela perfil do polÃ­tico | CriaÃ§Ã£o da tela do perfil do polÃ­tico | 242125 | Sprint 2 | 2019-10-08 | 2019-10-29 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 13.0 |  | 20.0 |  | 33.0 | 1571146981178 | 0 | 1571146981179 | 2019-10-15 13:43:01.202945+00:00 | 2019-11-11 23:59:59.529657+00:00 | 2019-11-11 23:59:59.555257+00:00 | False | False | 0 | [5 empty] | [] | 0
3011060 | 18 | FunÃ§Ã£o seguir polÃ­tico | Cria funÃ§Ã£o que permite seguir um polÃ­tico | 245358 | Sprint 3 | 2019-10-30 | 2019-11-20 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 20.0 |  | 13.0 |  | 33.0 | 1571147205144 | 0 | 1571147205144 | 2019-10-15 13:46:45.163272+00:00 | 2019-11-12 00:00:24.706800+00:00 | 2019-11-12 00:00:24.727916+00:00 | False | False | 0 | [5 empty] | [] | 0
3011063 | 19 | NotificaÃ§Ãµes para seguidores | FunÃ§Ã£o que envia notificaÃ§Ãµes apenas para os seguidores | 245358 | Sprint 3 | 2019-10-30 | 2019-11-20 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 20.0 |  |  |  | 20.0 | 1571147252092 | 1 | 1571147252093 | 2019-10-15 13:47:32.118906+00:00 | 2019-11-12 00:00:39.039863+00:00 | 2019-11-12 00:00:39.061451+00:00 | False | False | 0 | [5 empty] | [] | 0
3011064 | 20 | Tela de usuÃ¡rio | Tela do perfil de usuÃ¡rio | 245358 | Sprint 3 | 2019-10-30 | 2019-11-20 | diegokremer | Diego Kremer | diegokremer | Diego Kremer | diegokremer | Diego Kremer | Done | True | 13.0 |  | 20.0 |  | 33.0 | 1571147290882 | 2 | 1571147290882 | 2019-10-15 13:48:10.913518+00:00 | 2019-11-12 00:00:53.326066+00:00 | 2019-11-12 00:00:53.347685+00:00 | False | False | 0 | [5 empty] | [] | 0